## Week 1
Task | Time Est. | Risk | Who | Total Time | % Complete | Code Review
IEEEfp get references |  |  | Xavier
IEEEfp ranges and precision |  |  | Ali
GCC compiler option choices |  |  | Xavier
Get C programming standards |  |  | Xavier
Relative and absolute error |  |  | Ali
Initial QuadSolver and references | 1 hr | 2 | Nate
Set up group GitHub account | 5 min | 1 | Nate | 5 min | 100%
Set up Slack channel | 5 min | 1 | Nate | 5 min | 100%
Spike for validating input and displaying output |  |  | Xavier
Write stories |  |  | Nate, Xavier, Ali