## Week 1
Task | Time Est. | Risk | Who | Total Time | % Complete | Code Review | Notes
Logging Spike | 15 min | 2 | Nate | 15 min | 100%
Write rline | 20 min | 2 | Nate | 30 min | 100%
Write stories | 15 min | 1
Write validate | 1 hr |  | Ali | 1 hr | 100%
Restructure dirs | 15 min | 1 | Xavier/Ali | 30 min | 100%
test rline | 15 min | 2 | Nate | 15 min | 100%
test validate | 10 min |  | Ali | 5 min | 100%
adding documentation
Readme structure in coding standard | 10 min | 1 | Xavier | 10 min | 100%