## Week 1
Task | Time Est. | Risk | Who | Total Time | % Complete | Code Review | Notes
Do a spike on unit testing in C | 30 min | 3 | Nate | 30 min | 50%
Write unit tests for rline
Write unit test for validate
Spike: macros to determine normalized numbers, Inf, NaN
Add header for rline | 10 min | 1 | Nate | 10 min | 100%
Migrate logging to its own module | 15 min | 2 | Nate | 20 min | 100%
Add header for validate
Create a main? | 15 min | 2 | Nate | 20 min | 100%
Fix makefile linking heirarchy | 1 hr | 4 | Nate, Ali, Xavier |  | 50%