## Sheet 1
Task | Time Est. | Risk | Who | Total Time | % Complete | Code Review | Notes
Write unit tests for rline
Write unit test for validate |  | 3 | Ali |  | 10% |  | Looked up the testing, not done yet, might push this to next week
Spike: macros to determine normalized numbers, Inf, NaN | 1 hr | 2 | Ali | 30 min | 100% |  | figured out the
Write format_line | 1 hr | 2 | Xavier | 30 min | 100% | Ali | Not currently integrated
Unit test format_line | 1 hr | 3 | Xavier | 10 min | 20% |  | Started the testing, but have not fully covered the code yet
Add validate to main along with header | 10 min | 2 | Nate | 30 min | 100% | Xavier
changed data types of a, b, and c to floats and reworked the header file | 2 mins | 1 | Ali | 2 min | 100% | Xavier
figure out more spikes for validate_line functions | 30 mins | 2 | Ali | 30 min | 100%
start integration on quad solver | 1 hr | 3 | Nate | 40 min | 100% | Xavier | took code from previous spike; need to replace doubles in validate.
Test makefile structure to make sure it works at top level | 15 min | 2 | Nate | 15 min | 100% | Xavier | make clean does not clean subdirs.