## Sheet 1
Team Name | Ali, Nathan, Xavier |  |  |  |  | Date |  | Week of Feb 19
Task | Time Est. | Risk | Who | Total Time | % Complete | Code Review | Notes
write unit test for rline | 2 hr | 3 | Nate |  |  |  | push to next week for Kapenga's lecture on unit testing
Write unit test for validate | 2 hr | 3 | Ali |  | 10% |  | Looked up the testing, not done yet, might push this to next week
add build directory and include the compiled files | 10 min | 2 | Ali | 10 min | 100%
Extensive spike on CUnit | 1 hr | 3 | Xavier |  |  |  | Started with code from CUnit's site, might push to next week
Unit test format_line | 1 hr | 3 | Xavier | 10 min | 20% |  | Started the testing, but have not fully covered the code yet
Add maintainence, security and testing to docs | 1 hr | 2 | Ali/Xavier | 30min | 50%
Create a deploy command that creates a tar file of the project | 15 min | 2 | Nate | 15 min | 100%
write outline function | 10 min | 1 | Xavier | 10 min | 100%
Finish quad_solver main | 1 hr |  | Ali/Nate | 30 min | 75% |  | put in format line and outline and make sure it runs
Look into implementation of IEEEfp for q_solve | 2 hr | 3 | Nate
Update spikes for validation function | 30 min | 3 | Ali | 30min |  |  | update the spike functions since we are updating src functions