## Sheet1
Team Names | Ali, Nathan, Xavier |  |  |  |  | Date |  | Week of Mar 12
Task | Time Est. | Risk | Who | Total Time | % Complete | Code Review | Notes
Unit test for r_line | 30 min | 4 | Ali | 15 min | 100% | Nate
Unit test for validate_line | 1 hr | 5 | Ali | 1 hr | 100% | Nate
Add test commands for top level makefile | 10 min | 2 | Nate | 5 min | 100% | Ali
Unit test for q_solve | 2 hrs | 4 | Nate/Ali | 2 hrs | 100% | Ali
Integrate format line | 30 min | 3 | Xavier | 30 min | 90% |  | just need to check conflicts with system tests
Integrate outline | 30 min | 3 | Xavier | 30 min | 90% |  | just need to check conflicts with system tests
Unit test for format line | 45 min | 3 | Xavier | 30 min | 100%
Unit test for outline | 15 min | 2 | Xavier | 20 min | 100%
f