## Sheet1
Team Names | Ali, Nathan, Xavier |  |  |  |  | Date | Week of Mar 19
GitHub Repository: | https://github.com/wmu-seniordesign-2018/quadratic-solver
Task | Time Est. | Risk | Who | Total Time | % Complete | Code Review | Notes
Finish unit testing for format line | 45 min | 3 | Xavier | 30 min | 100%
Finish unit testing for outline | 15 min | 2 | Xavier | 20 min | 100%
Clean up code and printing of all unit tests | 1 hr | 3 | Ali | 45 min | 90% |  | i did not check qsolve, format_line or outline
Clean up READMEs (add instructions, more detail) | 30 min | 1 | Nate | 30 min | 100%
Move unit tests for format line and outline to /test and update makefile | 20 min | 2 | Nate | 20 min | 100% | Xavier
Run system tests of the program
Write use cases for usability testing | 1 hr | 3 | Ali
added log_output() to validate_line() | 10 min | 2 | Ali | 10 min | 100% | Xavier | purpose is to log the numbers after validating them
added a loop in quad_solver to prompt the user for numbers | 20 min | 3 | Ali | 20 min | 100% | Xavier
in each dir list whats inside those dirs and subdirs | 30 min | 1
maybe change the name of build folder to distribution instead? | 10 min | 1
add include folder in src and have all the includes there instead | 20 min | 1 | Ali | 20 min | 100%