## Week 1
Stories | Time Est. | Risk | Total Time | % Complete
Team will put together lists of standards for the program | 1 hr | 1
Team will create a module in its own directory for input | 30 min | 2
Engineer will be able to input values in scientific notation | 30 min | 2
Team will create a module in its own directory for validation | 30 min | 2
Team will create a module in its own directory for the quadratic solver | 2 hrs | 4
Team will develop a way to square root without losing floating point decimal places | 1 hr | 5
Team will develop a function to determine if the roots are bad, or if at any point a solution doesn't present itself as real | 1 hr | 5
Engineer will receive a double solution if one exists | 30 min | 3
Team will perform extensive unit testing on individual modules | 3 hrs | 4
Team will handle recovery if solution is INF or NAN | 30 min | 3
Team will create a module in its own directory for output formatting | 1 hr | 3
Team will create a module in its own directory for outputting the solution to the Engineer | 30 min | 2
Release 1