## Week 1
Task | Time Est. | Risk | Who | Total Time | % Complete | Code Review
IEEEfp get references |  |  | Xavier
IEEEfp ranges and precision | 20 min |  | Ali | 20 min | 100%
GCC compiler option choices |  |  | Xavier
Get C programming standards |  |  | Xavier
Relative and absolute error | 20 min |  | Ali | 20 min | 100%
Initial QuadSolver and references | 1 hr | 2 | Nate | 30 min | 100%
Set up group GitHub account | 5 min | 1 | Nate | 5 min | 100%
Set up Slack channel | 5 min | 1 | Nate | 5 min | 100%
Spike for validating input and displaying output |  |  | Xavier
Write stories | 15 min | 1 | Nate | 20 min | 100%